## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
K | 7900 | 7950 | -50 | 3800 | 4400 | -600 | 2600 | 1900 | 700 | 700 | 850 | -150 | 800 | 800 | 0
Andrew | 8400 | 4272 | 4128 | 3800 | 72 | 3728 | 2600 | 1900 | 700 | 1200 | 1500 | -300 | 800 | 800 | 0
Meghan | 6900 | 4400 | 2500 | 3400 | 1600 | 1800 | 2600 | 1900 | 700 | 100 | 100 | 0 | 800 | 800 | 0
David | 7900 | 4300 | 3600 | 3500 | 500 | 3000 | 2600 | 1900 | 700 | 1000 | 1100 | -100 | 800 | 800 | 0
Mathew | 6600 | 6400 | 200 | 2500 | 3100 | -600 | 2600 | 1900 | 700 | 700 | 600 | 100 | 800 | 800 | 0
Jon | 9100 | 5600 | 3500 | 5000 | 2300 | 2700 | 2600 | 1900 | 700 | 700 | 600 | 100 | 800 | 800 | 0
Rebecca | 8600 | 4131 | 4469 | 4000 | 31 | 3969 | 2600 | 1900 | 700 | 1200 | 1400 | -200 | 800 | 800 | 0
Total | 55400 | 37053 | 18347 | 26000 | 12003 | 13997 | 18200 | 13300 | 4900 | 5600 | 6150 | -550 | 5600 | 5600 | 0

## Gantt
Employee | predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
K |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Player design and prototype | 5 | 5 | complete | bar: key 1 to planned 5
Testing | 3 | 8 | complete | bar: planned 6 to planned 14
Entity and states | 6 | 7 | complete | bar: planned 15 to planned 18
Item superclass design | 3 | 4 | complete | bar: planned 15 to planned 18
Item subclass design | 4 | 4 | complete | bar: planned 18 to planned 21
Item interactions function | 4 | 6 | complete | bar: planned 22 to planned 27
Programming | 5 |  | planned | bar: planned 28 to planned 32
Documentation | 4 | 10 | complete | bar: planned 33 to planned 42
Implementation | 4 |  | planned | bar: planned 43 to planned 46
totals | 38 | 44
Andrew
Player state machine | 6 | 9 | complete | bar: key 1 to planned 6
Player animations | 5 | 8 | complete | bar: planned 7 to planned 11
Sprites | 4 | 8 | complete | bar: planned 12 to planned 15
Testing | 3 | 20 | complete | bar: planned 16 to planned 18
Enemy state machine | 6 | 7 | complete | bar: planned 19 to planned 22
Enemy animations | 5 | 11 | complete | bar: planned 23 to planned 33
Programming | 5 | 6 | complete | bar: planned 28 to planned 33
Integration | 4 | 3 | complete | bar: planned 34 to planned 36
totals | 38 | 72
Meghan
Sound and music creation | 6 | 6 | complete | bar: key 1 to planned 6
Testing | 3 | 10 | complete | bar: planned 7 to planned 10
Sounds and music exportation | 3 |  | this week | bar: planned 11 to planned 13
Creating loops | 5 |  | this week | bar: planned 14 to planned 18
Designing easter eggs | 3 |  | planned | bar: planned 19 to planned 21
Importing characteristics | 4 |  | planned | bar: planned 22 to planned 25
Easter egg effects | 4 |  | planned | bar: planned 26 to planned 29
Programming | 6 |  | planned | bar: planned 30 to planned 35
Integration | 3 |  | planned | bar: planned 36 to planned 38
totals | 34 | 16
David
Setting up Unity | 1 | 1 | complete | bar: key 1
Testing | 3 | 6 | complete | bar: complete 2 to this week 3
Requirements Collection | 8 |  | this week | bar: planned 4 to planned 11
Sprite Aggregation | 4 |  | this week | bar: planned 12 to planned 15
Entity and states | 4 | 15 | complete | bar: planned 16 to planned 21
Enemy centric functions | 4 |  | planned | bar: planned 20 to planned 23
Enemy data storage | 3 |  | planned | bar: planned 20 to planned 22
Enemy interaction functions | 4 | 4 | complete | bar: planned 24 to planned 27
Integration | 4 |  | planned | bar: planned 28 to planned 31
totals | 35 | 26
Matthew
Basic level functionality | 4 | 12 | complete | bar: key 1 to planned 12
Map design | 2 | 2 | complete | bar: planned 13 to planned 14
Testing | 4 | 12 | complete | bar: planned 15 to planned 23
Entity creation | 2 |  | this week | bar: planned 24 to planned 25
Powerup locations | 3 |  | planned | bar: planned 26 to planned 28
Checkpoints | 2 |  | planned | bar: planned 26 to planned 27
Programming | 7 | 5 | this week | bar: planned 29 to planned 35
Installation | 1 |  | planned | bar: planned 36
totals | 25 | 31
Jon
Required specifications | 4 | 4 | complete | bar: key 1 to planned 4
Powerups | 3 | 3 | complete | bar: planned 5 to planned 7
Button Design | 6 | 6 | complete | bar: planned 8 to planned 13
Menu layout design | 3 | 3 | complete | bar: planned 14 to planned 16
Testing/trial and error | 10 | 7 | this week | bar: planned 17 to planned 23
Group collaboration | 6 |  | planned | bar: planned 24 to planned 29
Group collaboration | 5 |  | planned | bar: planned 30 to planned 34
Implementation | 10 |  | planned | bar: planned 35 to planned 44
Finalization | 3 |  | planned | bar: planned 45 to planned 47
totals | 50 | 23
Rebecca
Check player health program | 4 | 5 | complete | bar: key 1 to planned 5
Make health bar move | 3 | 7 | complete | bar: planned 6 to planned 7
Testing | 5 | 11 | complete | bar: planned 8 to planned 10
Check player location | 4 |  | this week | bar: planned 11 to planned 14
Mini map functionality | 6 |  | this week | bar: planned 15 to planned 20
Check enemy contact | 3 | 2 | this week | bar: planned 21 to planned 23
Mission display | 2 |  | this week | bar: planned 24 to planned 25
HUD layout | 3 | 4 | this week | bar: planned 26 to planned 28
Installation | 5 |  | planned | bar: planned 29 to planned 33
Artwork | 5 | 2 | planned | bar: planned 34 to planned 38
totals | 40 | 31
group totals (hrs) | 145 | 158
group totals ($) | 14500 | 15800

## Team Mate Delverables
TL 1 Deliverables |  |  | TL 2 Deliverables |  |  | TL 3 Deliverables |  | TL 4 Deliverables | TL 5 Deliverables | TL 6 Deliverables
Date Due: Feb 13th |  |  | Date Due: Jan 30th |  |  | Date Due: Mar 5th |  | Date Due: Mar 26th | Date Due: Apr 2nd | Date Due: Apr 11th
Location: |  |  | Location: |  |  | Location: |  | Location: | Location: | Location:
Deliverable Tracker
| K | Andew | Meghan | Matthew | David | Jon | Rebecca
TL 1 |  |  | ü
TL 2 | ü |  |  | ü
TL 3 | [5 empty] | ü
TL 4
TL 5
TL 6
ü

## Meetings
| Date | Feb. 3 | Feb. 12 | 2024-03-30
| Purpose | First Meeting | RFP Meeting | Patterns, roles | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 6 | 1 | 8 | 26
K |  | ü | ü | ü
Andrew |  | ü | ü | ü
Meghan |  | ü | ü | ü
David |  | ü | ü | ü
Matthew |  | ü | ü | ü
Jon |  | ü | ü
Rebecca |  | ü | ü
Total | 0 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
K | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6.5 | bar: 3 to 7
| Subtotal | 7 | 8.5
Andrew | Individual schedule | 2 | 3 | bar: 1 to 3
| Champion | 10 | 12 | bar: 4 to 15
| Subtotal | 12 | 15
Meghan | Individual schedule | 1 | 1 | bar: 1
Champion | bar: 2 to 6
| Subtotal | 1 | 1
David | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 8 | 9 | bar: 3 to 11
| Subtotal | 10 | 11
Matthew | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 3 to 7
| Subtotal | 7 | 6
Jon | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 3 to 6
| Subtotal | 7 | 6
Rebecca | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 10 | 12 | bar: 3 to 14
| Subtotal | 12 | 14
| Total | 44 | 47.5

## Overhead
| K | Andrew | Meghan | Matthew | Jon | Rebecca | David
Training | 8 | 8 | 8 | 8 | 8 | 8 | 8
SA Preesentation Prep | 8 | 5 | 3 | 6 | 2 | 3 | 2
Software Specialist Presnetaion Prep |  | 3 |  |  | 2 | 3 | 3
Team Lead Presentation Prep | 10 |  | 10 | 8 | 6 | 8
Oral Exam Prep | 20 | 1 |  | 3 |  | 17
Post Mortum Presentation Prep
Total | 46 | 17 | 21 | 25 | 18 | 39 | 13